## Table2
Year |  | 2016 | [8 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
Month |  | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Clean room for Hayabusa2
Preliminary design
Contract
Detail design
Room construction
Piping installation
Alert system installation
Clean chamber for Hayabusa2 (CC3-1 and CC3-2)
Preliminary design
Contract
Detail design
Manufacture
Installation
Clean chamber for Hayabusa2 (CC3-3, CC4-1 and CC4-2)
Preliminary design
Contract
Detail design
Manufacture
Installation
Comprehensive functional check
Rehearsal
Refurbish
Sample Return

## Table4
| 2019 | [11 empty] | 2020
Items | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Container opening system | 2020 Apr: Facility lockdown due to COVID-19; 2020 Dec: Hayabusa2 Sample Return
CC3-1 ~ CC3-3
CC3-3 ~ CC4-2
Balance
Optical microscope
FT-IR
MicrOmega
Visible spectrometer
Chamber
Installation
Instrument
Installation
Cleanliness
test
Baking
Rehearsal
Rehearsal
Baking
Rehearsal
Rehearsal
Rehearsal
Rehearsal
Rehearsal
Rehearsal
Rehearsal
Rehearsal
Rehearsal
Rehearsal
Rehearsal
Instrument
Installation
Instrument
Installation
Rehearsal
Image analysis training & test
Image aquisition test
Test measurement
meeting & designing
Test & Rehearsal
Rehearsal
test &
calibration
Rehearsal
Chamber
Installation
Operation
training in IAS
Test measurement
Instrument installation
and test measurment
Baking
Cable revision
Tare measurement
Test, calibration, baking
Protyping & test